PoultryOS

Build Plan & Setup Guide

v1.0  |  Day-by-Day Execution Guide  |  April 2026

| Strategy | Total weeks | Effort | Outcome |
| --- | --- | --- | --- |
| 2-developer parallel: Mobile + Web | 18 weeks (4.5 months) | 8+ hrs/day each | Public launch v2.0 with all 16 features |

📘 This guide is the operating manual for your team. Use it alongside PRD v2.0 and TRD v2.0. Print this; check off tasks daily.

✅ 1. Pre-Build Checklist (Before Day 1)

Complete these before writing a single line of code. Some have approval lead times — start them ASAP.

### Accounts to create

| Service | URL | Cost | Lead time |
| --- | --- | --- | --- |
| Supabase | supabase.com | Free → $25/mo | Instant |
| Vercel | vercel.com | Free | Instant (have account) |
| Expo + EAS | expo.dev | Free → $29/mo | Instant |
| Google Play Developer | play.google.com/console | $25 one-time | Have account |
| MSG91 (SMS OTP) | msg91.com | Pay-as-you-go | 1–2 days for KYC |
| AiSensy (WhatsApp) | aisensy.com | ₹1,000/mo | 3–7 days for Meta verification |
| OpenWeatherMap | openweathermap.org | Free up to 1k calls/day | Instant |
| Razorpay | razorpay.com | 2% per txn | 1–3 days KYC for live mode |
| GitHub | github.com | Free | Instant |
| Anthropic (Claude API, future) | console.anthropic.com | Pay-as-you-go | Instant |

### Tools to install on dev machines

- Node.js 20+ (for Expo, Next.js, scripts)

- pnpm or npm (package manager)

- Expo CLI: npm install -g eas-cli

- Supabase CLI: npm install -g supabase

- Cursor IDE (cursor.com) — best for AI coding with Claude

- Android Studio (for Android emulator) OR a physical Redmi 9A / Samsung A-series for testing

- VSCode (backup IDE) with Tailwind, ESLint, Prettier extensions

- Postman or Bruno (for testing Edge Functions and APIs)

- Figma (for any quick UI mockups; v0.dev for AI-generated UI)

### Pre-Day-1 documents to prepare

- AiSensy WhatsApp template drafts (6 templates listed in TRD Section 8)

- Razorpay business documents: PAN, GSTIN, bank account, business proof for KYC

- Privacy policy draft (use Termly.io or similar to generate)

- Terms of service draft

- App icon (1024x1024 PNG) and splash screen artwork

- Google Play Store assets: feature graphic (1024x500), 8 screenshots, short + long description

⚠️ Critical: Submit AiSensy WhatsApp templates and Razorpay KYC on Day 1. They take 3–7 days. If you wait until Phase 2, you'll be blocked.

👥 2. Two-Developer Split

### Recommended ownership

| Developer A: Mobile + Backend | Developer B: Web + Backend |
| --- | --- |
| Expo project setup | Next.js project setup |
| All mobile screens (24) | All web screens (10) |
| Daily log offline queue (AsyncStorage) | Web reports + PDF export |
| Push notifications setup (Expo) | Public traceability page (/trace/[token]) |
| Mobile-specific UPI QR generation | Razorpay subscription billing UI + flow |
| WhatsApp share flow from mobile | Multi-farm consolidated dashboard |
| Supabase tables + RLS (shared) | Edge Functions (shared) |
| EAS Build + Play Store submission | Vercel deployment + custom domain |

### Shared work (both devs)

- Supabase schema design — review together; one person writes the migration

- RLS policies — pair on the first one; one person finishes the rest

- Edge Functions — split by function; both review each other’s

- Type definitions (shared types/ folder if monorepo) — keep in sync

- End-to-end testing in Phase 5

### Daily sync ritual (15 minutes)

- 9:00 AM — Daily standup: yesterday’s wins, today’s plan, blockers

- 9:15 AM — Code

- 1:00 PM — Lunch

- 5:00 PM — Quick demo (5 min) of what each dev built; merge PRs

- 5:15 PM — Continue or wrap

📅 3. Week-by-Week Build Plan (18 weeks)

### Week 1: Foundation

| Day | Dev A (Mobile) | Dev B (Web) |
| --- | --- | --- |
| Mon | Initialise Expo project; install all packages from TRD Section 3 | Initialise Next.js + shadcn/ui; install all packages |
| Tue | Set up expo-router; configure Supabase client; secure storage | Set up Supabase SSR; auth helpers; layout shell |
| Wed | Both: Run all v1+v2 CREATE TABLE in Supabase SQL Editor; enable RLS | Same: Apply RLS policies; create storage buckets |
| Thu | Mobile login screen (OTP + email); MSG91 OTP integration | Web login screen; Supabase email auth |
| Fri | Onboarding wizard (5 screens): farm type, farm name, sheds, batch, WhatsApp opt-in | Onboarding wizard (web equivalent) |
| Sat | Dashboard skeleton; KPI cards; bottom nav | Dashboard skeleton; sidebar nav; user farm switcher |
| Sun | Buffer: catch up, deploy first APK to Expo Go for testing | Buffer: deploy first preview to Vercel |

### Week 2: Farm management + Batches

| Day | Dev A (Mobile) | Dev B (Web) |
| --- | --- | --- |
| Mon–Tue | Farm settings screen; shed CRUD; user invite + roles | Farm settings; shed CRUD; user management |
| Wed–Thu | Batch creation screen; flock list; batch detail view | Batch creation; flock list; batch detail |
| Fri | fetch-weather-data Edge Function (paired) | Continue Edge Function; integrate OpenWeatherMap API |
| Sat | Weather widget on dashboard (current temp + 3-day) | Weather widget on web dashboard |
| Sun | Buffer | Buffer |

### Week 3: Daily log + offline queue

| Day | Dev A (Mobile) | Dev B (Web) |
| --- | --- | --- |
| Mon–Wed | Daily log entry screen; AsyncStorage offline queue; sync logic on reconnect | Web: daily log entry view; sync indicator |
| Thu | DB triggers: update_batch_bird_count, check_mortality_spike, deduct_feed_inventory | Pair on triggers; test with seed data |
| Fri | send-push-notification Edge Function; mortality alert end-to-end test | Verify mortality alert in web dashboard |
| Sat–Sun | Buffer + Phase 1 gate testing: worker logs <60s; offline syncs | Same |

### Weeks 4–7: Core ops + WhatsApp integration

- Wk 4: Health incident form, vaccinations scheduler, vaccination reminder cron

- Wk 5: Inventory module; low-stock alert cron; AiSensy WhatsApp template approval should be done by now

- Wk 5–6: send-whatsapp-message Edge Function; aisensy-webhook; wire up alerts to WhatsApp

- Wk 6: send-daily-digest cron at 8 PM IST; STOP/RESUME inbound handling

- Wk 7: send-heat-stress-alert; weather_alerts table; mitigation actions UI; Phase 2 gate

### Weeks 8–10: Financials + UPI Khata

- Wk 8: Income/expense entry screens; KPI dashboard; charts (Victory Native + Recharts)

- Wk 9: Buyers list + detail screens; UPI QR generation (BHIM URI scheme); buyer ledger

- Wk 10: send-payment-reminders cron; Razorpay UPI Collect integration; auto-confirm flow; P&L screens; Phase 3 gate

### Weeks 11–13: Standout features

- Wk 11: fetch-market-prices Edge Function; price strip on dashboard; manual override

- Wk 12: 14-day price chart; profit calculator card on batch detail

- Wk 13: Traceability records auto-population; QR generation; generate-traceability-pdf; PDF share via WhatsApp; Phase 4 gate

### Weeks 14–18: Contract farming + Web + Billing + Launch

- Wk 14: Seed integrators table with Suguna, Venkateshwara, Skylark, IB Group tariff cards; contract module screens

- Wk 15: contract_cycles tracking; calculate-contract-settlement Edge Function; settlement reconciliation report

- Wk 16: Web dashboard polish; reports + export; Razorpay subscription flow; freemium gates UI

- Wk 17: Multi-farm consolidated dashboard (web); end-to-end testing with 5 beta farms (incl. 2 contract farms)

- Wk 18: Bug fixing; Play Store submission; production deployment; soft launch; Phase 5 gate

🤖 4. AI Coding Workflow

This is how to actually use Claude / Cursor / Bolt to build PoultryOS efficiently.

### Step-by-step for any new feature

- Open Cursor; create a new file with the feature name (e.g., screens/buyers/BuyerDetail.tsx)

- Copy the relevant section from PRD v2.0 (feature spec) into the comment block at the top

- Copy the relevant section from TRD v2.0 (table schema, RLS policy, API patterns) into the comment block

- Prompt Claude/Cursor: "Build this screen following the PRD spec and TRD schema above. Use react-native-paper components. Match the design system: brand blue #1A56DB, Inter font."

- Review generated code for: RLS compliance (every query scoped to current farm), error handling, offline tolerance

- Test on Android emulator or Redmi 9A device

- Commit with descriptive message; push to GitHub; deploy preview

### Tools per task

| Task | Best AI tool | Why |
| --- | --- | --- |
| UI components (web) | v0.dev | Generates shadcn/ui + Tailwind natively |
| UI components (mobile) | Claude in Cursor | Knows react-native-paper well |
| Database schemas | Claude (paste TRD into Cursor) | Generates SQL CREATE TABLE + RLS verbatim |
| Edge Functions (Deno) | Claude in Cursor | Best for TypeScript Deno + Supabase |
| Bug fixes | Cursor agent mode | Reads multiple files; finds root cause |
| Refactoring | Cursor agent mode | Multi-file edits |
| WhatsApp template content | Claude (chat) | Best at writing concise, clear messages |

### Rules of engagement with AI

- Always paste the relevant TRD table schema before asking for code — don’t make AI guess column names

- Always specify the role (Owner / Worker / Vet) before asking for permission-gated UI

- Review every Supabase query for RLS compliance; AI sometimes forgets RLS

- Test offline behaviour manually — AI cannot test this for you

- For WhatsApp templates: never let AI hallucinate template IDs; use the exact ones approved by AiSensy

📝 5. Key Decisions Log

| Decision | Choice | Rationale |
| --- | --- | --- |
| Auth method | Mobile OTP primary, email secondary | Indian users prefer OTP; reduces support burden |
| WhatsApp provider | AiSensy | Cheaper than Gupshup; good Indian SLA |
| Weather provider | OpenWeatherMap free | Sufficient for 200 farms hourly; IMD has no public API |
| Charts library | Victory Native + Recharts | Best AI-tool support; performant on low-end Android |
| State management | Zustand | Minimal boilerplate; AI generates stores easily |
| UI library (mobile) | react-native-paper | Material Design 3; works on low-end; AI knows it well |
| UI library (web) | shadcn/ui | v0.dev generates it natively; copy-paste components |
| Form library | react-hook-form + zod | Type-safe; minimal re-renders |
| No AI in MVP | Rule-based intelligence only | Avoid LLM costs early; defer to Phase 6 when revenue is proven |
| UPI QR — client-side | BHIM URI scheme + react-native-qrcode-svg | Free; no API call; instant generation |
| Razorpay + UPI Collect | Use both | Subscriptions for SaaS billing; UPI Collect for buyer payments with auto-confirm |
| Offline scope | Daily log only | Most common offline use case; full sync is overkill for MVP |
| Deferred features | Vernacular voice, Vet marketplace, Loan marketplace, AI chatbot | Need user density or unproven ROI; revisit at 200 farms |

🚨 6. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| AiSensy WhatsApp template approval rejected | Medium | High (Phase 2 blocker) | Submit Day 1; have backup wording; follow Meta’s template guidelines strictly |
| Agmarknet website structure changes (breaks scraper) | Medium | Medium (price stops updating) | Daily test of scraper; manual override always available; show "price unavailable" gracefully |
| Razorpay live mode KYC delayed | Low | High (cannot accept payments) | Submit KYC Day 1; use test mode for development; have Stripe as fallback (but rebuild needed) |
| Low-end Android performance issues | Medium | High (target users excluded) | Test on Redmi 9A weekly; profile bundle size; lazy-load heavy screens |
| WhatsApp opt-in rate too low | Medium | Medium (digest feature underused) | Make opt-in clear during onboarding; show value prop ("Get daily reports on WhatsApp") |
| Contract integrators don’t adopt | High | Medium (B2B revenue path stalls) | Direct sales to integrators in Phase 5; demonstrate value with 10 contract growers first |
| Supabase outage | Low | Critical (entire app down) | Supabase has 99.9% SLA; offline queue ensures daily logs aren’t lost; status page monitoring |
| Heat-stress alert false positives | Medium | Medium (alert fatigue) | Calibrate threshold per breed; let owners customise; track acknowledgement rate |
| Beta users don’t convert to paid | Medium | High (no MRR) | Pricing research with beta users; consider launch discount; ensure paid features are genuinely valuable |
| Data loss on offline sync conflict | Low | Critical (farmer trust broken) | Last-write-wins is fine for daily logs (one entry per shed per day); UNIQUE constraint prevents duplicates |

🚀 7. Launch Checklist (Week 18)

### Technical readiness

- All Phase 1–5 features pass Definition of Done (TRD Section 12)

- Razorpay live mode active; subscription tested with real payment

- AiSensy templates approved; WhatsApp messages tested across all types

- Privacy policy + terms published in-app and on website

- App listed on Google Play Store (production track)

- Web app deployed to app.poultryos.com (or your domain)

- Public traceability pages working at poultryos.com/trace/[token]

- Database backups verified working

- Error monitoring set up (Sentry free tier)

- Analytics: PostHog free tier or Supabase native analytics

### Beta validation

- 5 beta farms used app for ≥14 consecutive days

- At least 2 contract farms tested settlement reconciliation

- At least 3 farms generated and shared traceability certificates

- At least 1 farm completed end-to-end UPI Collect with real buyer

- Zero P0 (critical) bugs open

- Beta NPS score collected; aim for >40

### Go-to-market

- Landing page live at poultryos.com with feature list, pricing, demo video

- 3-minute demo video recorded (mobile screen recording)

- WhatsApp Business profile set up (separate from app dispatch number) for support

- Pricing finalised: Free + ₹499/mo or ₹4,999/yr (suggest ₹5,499 with discount)

- Launch posts ready: LinkedIn, AgriTech communities, poultry farmer WhatsApp groups, Reddit r/IndianFarming

- ProductHunt launch scheduled (Tuesday 12:01 AM PT)

- First 10 farms onboarded manually with white-glove support to ensure success

🎯 8. Post-Launch Priorities (Months 5–6)

### Immediate (Month 5)

- Bug triage daily; respond to user feedback within 24 hours

- Track activation funnel: signup → first batch created → first daily log → 7-day retention

- Onboarding tweaks based on drop-off points

- First paid user celebration; share story on social

### Short-term (Month 6)

- Reach out to 1 integrator (Suguna or Venkateshwara) for B2B pilot

- Begin Phase 6: vernacular voice (Bhashini API — free for Indian languages)

- AI chatbot with Claude API for paid users

- iOS build (after first 100 paying farms)

### Targets at Month 6

- 300 active farms

- 60+ paid farms (₹30,000+ MRR)

- 85%+ WhatsApp opt-in rate

- 65%+ DAU/MAU ratio

- <6% monthly churn

PoultryOS Build Plan v1.0  —  April 2026  —  Print, post on the wall, check off daily

Use alongside PRD v2.0 and TRD v2.0. Ship something every Friday.